## High level plan
[Name] Review - High level plan
|  | MM/YY |  | MM/YY |  |  |  |  | MM/YY |  |  |  | MM/YY |  |  | MM/YY |  |  |  | MM/YY |  |  |  | MM/YY |  |  | MM/YY |  |  | MM/YY |  |  | MM/YY
|  | week comm. | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm | week comm
Start | Finish
Scope
Engage
Diagnose
Design & Test
Implement
Sustain

## Project Plan
|  | Engage | [11 empty] | Phase: | Scope | [6 empty] | Engage |  | Diagnose | Design | Implement | Sustain
|  | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | Week Commencing:
Review phase | Detailed activity: | 2023-02-06: Scope sign-off; 2023-02-13: Oxford Half Term; 2023-02-20: Gloucs Half Term; 2023-04-03: Easter (6 & 7/4 UAS Closure); 2023-04-10: Easter (10/4); 2023-04-24: Diagnose plan sign-off | Outputs
Scope | Define scope of the review /project | [12 empty] | Charter
| Confirm project team membership | [12 empty] | Charter
| Confirm governance arrangements | [12 empty] | Charter
| Stakeholder mapping | [12 empty] | Stakeholder map
| Define the appropriate levels of service (SAM) | [12 empty] | Service Assessment Model
| Create project plan | [12 empty] | Project Plan
Engage | Plan stakeholder engagement activities | [12 empty] | Communications and engagement plan
| Plan data collection | [12 empty] | Data plan
Diagnose | Plan for design activities | [12 empty] | Updated project plan
| Data gathering activities | [12 empty] | Analysed data and structure for design phase
| Write up findings | [12 empty] | Diganose report (evidence)
Design | Design activities to create design for the service | [12 empty] | Stakeholder feedback on the ideas/ proposals
| Write up recommendations | [12 empty] | Recommendations report
Implement | Create Implementation plan | [12 empty] | Implementation plan
Agree reporting arrangements
Agree changes to working practices
Sustain | Keeping in touch/ review point activities | [12 empty] | Keeping in touch (KIT) plan/ review schedule
Analyse stakeholder feedback
Make changes in response to feedback (if required)
Service Assessment Model | Draft SAM operating levels | bar: 2023-02-06 to 2023-02-27
Form Check & Test Group | bar: 2023-02-06 to 2023-02-27
Request SAM input from Karen Sergiou | bar: 2023-02-20 to 2023-02-27
SAM development w Project Team | bar: 2023-02-20 to 2023-02-27
Initial mapping of existing evidence eg Rachel M report, audit | bar: 2023-02-27 to 2023-03-06
SAM induction meeting with Check and Test grp | bar: 2023-02-27
SAM development workshops w Check and Test Group | bar: 2023-03-06
Review output and refine SAM with project team | bar: 2023-03-13 to 2023-03-20
Draft evidence map for how SAM elements will be assessed | bar: 2023-03-27 to 2023-04-17
Present SAM evidence plan to Oversight Board (meeting 2) | bar: 2023-04-24
Present drafted SAM to Co-Chairs for review | bar: 2023-03-27 to 2023-04-03
Refine SAM based on feedback | bar: 2023-04-10 to 2023-04-17
SAM sign-off by co-chairs | bar: 2023-04-10 to 2023-04-17
Present SAM to Oversight Board (meeting 2) | bar: 2023-04-17 to 2023-04-24
Request to co-chairs to review SAM level 5 to align with vision
Feedback from co-chairs on SAM L5 review
Resourcing - info gathering | Comms to DRs to pre-warn about request | bar: 2023-03-20 to 2023-03-27
Design and testing of spreadsheet and survey questions | bar: 2023-03-20 to 2023-03-27
Detailed distribution planning | bar: 2023-03-20 to 2023-03-27
Co-chair and project team review and feedback | bar: 2023-03-27 to 2023-04-10
Comms drafting for survey distribution | bar: 2023-04-10 to 2023-04-24
Finalise survey | bar: 2023-04-17 to 2023-04-24
Issue survey to Divisions | bar: 2023-04-24
Comms/engagement opportunities to note | MSD Finance and GPC (HoDs) | 2023-04-17: 18th
| MPLS GPC (HoDs) | 2023-04-24: 24th
| SSD HAFs meeting | 2023-04-24: 28th
MPLS Divisional board (HoDs)
| MSD HAFs meeting with DR | [13 empty] | 11th
| MPLS HAFs meeting with DR | [14 empty] | 18th
| MSD Finance and GPC (HoDs) | [14 empty] | 18th
| MPLS GPC (HoDs) - ITI presenting | [15 empty] | 22nd
| Cont Ed Strategic mgmnt board - ITI presenting | [15 empty] | 23rd
| SSD Planning and Resources Committee | [16 empty] | 30th
| Registrar's HAF meeting | [19 empty] | 21st
Registrar's HAF meeting
Finance year end roadshows
| MSD Finance and GPC (HoDs) - ITI presenting | [17 empty] | 6th
| SSD Divisional Board - ITI presenting | [17 empty] | 9th
| Hums Divisional Board - ITI presenting | [17 empty] | 9th
| MPLS Divisional Board - ITI presenting | [17 empty] | 9th
| SSD HAFs meeting | [17 empty] | 6th
| MSD HAFs meeting with DR | [17 empty] | 8th
| Registrar's SLT | [18 empty] | 14th
| MPLS GPC (HoDs) | [18 empty] | 16th
| MSD Divisional board | [19 empty] | 20th
| MPLS HAFs meeting with DR | [19 empty] | 22nd
| Hums Planning and Resources committee | [19 empty] | 23rd
| MSD HAFs meeting with DR | [21 empty] | 13th
| Services Sub committee - ITI presenting | [21 empty] | 18th

## SAM detailed (hidden)
|  | w/c 13 Feb | w/c 20 Feb |  |  |  | w/c 27 Feb |  |  |  | w/c 6 Mar | [33 empty] | w/c 13 Mar |  |  |  | w/c 20 Mar |  |  |  | w/c 27Mar |  |  |  | w/c 3 Apr |  |  |  | w/c 10 April |  |  |  | w/c 17 April |  |  |  | w/c 24 April
| Working days | Tue | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | Wed | Thu | Thu | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu | Mon | Tue | WEd | Thu
Service Assessment Model | Draft SAM operating levels
Feedback from Anne/Sarah on 1st draft SAM
Redraft SAM and prepare to brief project team
Email Check and Test group
Chase Check and Test members
Issue invitations to induction and workshops
Extend invitations to Oversight Board members
Request SAM input from Karen Sergiou
Continue to chase new pjt team members
Catch up sessions for missing pjt team members
Project team meetings - brief team and set tasks for between meetings
Write ppt and plan for induction meeting
Write workshop POST
Prepare workshop materials
Order tea/coffee
SAM induction meeting with Check and Test grp
Send advance materials re SAM
SAM development workshop w Check and Test Group
Back up workshop date if no Finance member for pjt team
Review workshop outputs
Redrafting
Refine SAM with project team
Present drafted SAM to Co-Chairs for review
Refine SAM based on feedback
SAM sign-off by co-chairs
Present SAM to Oversight Board (meeting 2)
Laura off w/c 27 Feb
Sam off w/c 20 Feb
RS out of Worcester st and WFH 24 Feb to 8 March
Project team dates still tbc with new members - Hannah Lingard absent 13/2 and 14/2 (unplanned)

## Info Gathering (hidden)
|  | w/c 13 Feb |  |  |  |  | w/c 20 Feb |  |  |  |  | w/c 27 Feb |  |  |  |  | w/c 6 Mar |  |  |  |  | w/c 13 Mar |  |  |  |  | w/c 20 Mar |  |  |  |  | w/c 27Mar |  |  |  |  | w/c 3 Apr |  |  |  |  | w/c 10 April |  |  |  |  | w/c 17 April |  |  |  |  | w/c 24 April
Engagement and Information Gathering | Working days | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Detailed stakeholder mapping | bar: w/c 20 Feb Mon to w/c 20 Feb Thu
Engagement with Divisional Research Leads | Engagement with Divisional Research Leads | bar: w/c 13 Feb Thu to w/c 13 Feb Fri
| Invites to meeting/interview | [55 empty] | Done | bar: w/c 13 Feb Thu to w/c 13 Feb Fri
| Follow up with non-responders | [55 empty] | Plan | bar: w/c 20 Feb Wed to w/c 20 Feb Thu
| Prep and circulate intro slide pack | [55 empty] | Meetings | bar: w/c 20 Feb Mon to w/c 20 Feb Tue
| Hold Divisional Research Lead Meetings: | [55 empty] | Key deadline/milestone | bar: w/c 20 Feb Thu; w/c 27 Feb Mon to w/c 27 Feb Fri
MPLS | bar: w/c 27 Feb Fri
MSD
HUMS | bar: w/c 27 Feb Wed
GLAM | bar: w/c 27 Feb Mon
SSD | bar: w/c 20 Feb Thu
Write up mtg findings/notes | bar: w/c 6 Mar Tue; w/c 6 Mar Thu to w/c 13 Mar Wed
Engagement with PIs and Key Prof. Srvcs Staff | Divisional engagement planning | bar: w/c 6 Mar Thu to w/c 13 Mar Thu
Prep comms for interview request | bar: w/c 6 Mar Fri to w/c 13 Mar Thu
Legitimate interest request for interviews | bar: w/c 13 Mar Tue; w/c 13 Mar Thu
Prep POST and key questions for interviews | bar: w/c 13 Mar Tue to w/c 13 Mar Thu
Confirm divisional approach and contact key groups | bar: w/c 13 Mar Thu to w/c 20 Mar Wed
Set up interviews | bar: w/c 20 Mar Mon to w/c 27Mar Fri; w/c 10 April Tue to w/c 10 April Fri
Hold PIs/key Prof. Srvcs. Staff interviews: | bar: w/c 27Mar Mon to w/c 27Mar Fri; w/c 10 April Tue to w/c 24 April Fri
[expand section when identified] | bar: w/c 27Mar Mon to w/c 27Mar Fri; w/c 10 April Tue to w/c 24 April Fri
Write up mtg findings/notes | bar: w/c 27Mar Mon to w/c 27Mar Fri; w/c 10 April Tue to w/c 24 April Fri
Identify themes and incorporate into diagnose phase
Staffing and Activity Data Collection (Resource Audit) | Survey Design - Questions / Structure | bar: w/c 13 Mar Mon to w/c 27Mar Fri
Prep comms for survey request | bar: w/c 20 Mar Mon to w/c 20 Mar Fri
Survey Design - set up - JISC | bar: w/c 27Mar Mon to w/c 27Mar Fri
RUN Survey | bar: w/c 27Mar Wed to w/c 27Mar Fri; w/c 10 April Tue to w/c 17 April Fri
Follow up with non-responders | bar: w/c 17 April Mon to w/c 17 April Fri
Analyse survey results | bar: w/c 17 April Mon to w/c 24 April Wed
Prep slide deck/analysis for OB2 | bar: w/c 17 April Fri to w/c 24 April Wed
Oversight Board Mtg 2 - 27/4 | bar: w/c 24 April Thu

## Process Improvement (hidden)
|  | w/c 27 Feb |  |  |  |  | w/c 6 Mar |  |  |  |  | w/c 13 Mar |  |  |  |  | w/c 20 Mar |  |  |  |  | w/c 27Mar |  |  |  |  | w/c 3 Apr |  |  |  |  | w/c 10 April |  |  |  |  | w/c 17 April |  |  |  |  | w/c 24 April |  |  |  |  | w/c 1 May |  |  |  |  | w/c 8 May |  |  |  |  | w/c 15 May
Process Improvement | Working days | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Detailed stakeholder mapping
Katherine Gardiner meetings | bar: w/c 27 Feb Tue; w/c 27Mar Tue
Mtg w Cat Temple | bar: w/c 13 Mar Mon
Project team process review planning | bar: w/c 13 Mar Thu; w/c 20 Mar Mon to w/c 20 Mar Thu
Project team confirm areas for priority review [tbd] | bar: w/c 20 Mar Thu
ROPOG/Check and Test Process review | ROPOG meeting | bar: w/c 27Mar Wed
Comms planning for PUG/C&T group re workstream | bar: w/c 20 Mar Mon to w/c 20 Mar Fri
Form PUG | bar: w/c 10 April Tue to w/c 17 April Wed
Invite PUG and C&T group to workshop(s) [no. tbd] | bar: w/c 17 April Mon to w/c 17 April Fri
Confirm attendance and workshop plans | bar: w/c 17 April Mon to w/c 24 April Fri
Update OB on process improvement workstream planning | bar: w/c 24 April Wed to w/c 24 April Thu
Hold workshops [no. tbd] | bar: w/c 1 May Tue to w/c 1 May Fri; w/c 8 May Tue to w/c 15 May Fri
Themes, Wastes, Improvements captured | bar: w/c 8 May Tue to w/c 15 May Fri
Oversight Board Mtg 2 - 27/4 | bar: w/c 24 April Thu

## zzOLD-draft High Level Plan (hidden)
| Phase: | Scope | [9 empty] | Engage | [11 empty] | Diagnose | [11 empty] | Review Outputs |  |  |  | Design | [10 empty] | Implement
Week commencing: | time axis 2022-11-21 to 2023-11-20
[6 empty] | Christmas | Bank Hol |  |  |  | Scope sign-off | Scope sign-off | Oxford Half Term | Gloucs Half Term |  |  |  |  | Diagnose plan sign-off | Easter | Easter |  |  | Bank Hol | Bank Hol |  |  | Bank Hol Half Term | [5 empty] | CI Conf | Evidence Report | Summer | Summer | Summer | Summer | Summer | Bank Hol Summer | [7 empty] | Half Term | Options Report |  |  | Recommendations Rpt & Implementation Plan
Governance | OB Meetings | 2023-07-24: Oversight Board to review and consider outcomes of Diagnose Phase
Co-Chair Meetings | bar: 2022-12-05; 2023-01-02; 2023-01-16 to 2023-01-23; 2023-02-06; 2023-02-20; 2023-03-06; 2023-03-20; 2023-04-03; 2023-04-17; 2023-05-01; 2023-05-15; 2023-05-29; 2023-06-12; 2023-06-26; 2023-07-10; 2023-08-21; 2023-09-04; 2023-09-18; 2023-10-02; 2023-10-16; 2023-10-30; 2023-11-13 to 2023-11-20
Focus MPRs | bar: 2022-11-28; 2023-01-09; 2023-01-30; 2023-02-27; 2023-04-10; 2023-05-01; 2023-05-29; 2023-07-03; 2023-09-04; 2023-10-02; 2023-10-30
Project Start up | Identify and appoint Sponsor | bar: 2022-11-21 to 2022-11-28
Identify and appoint Co-Chairs | bar: 2022-11-21; 2022-12-05
Identify and invite Oversight Board Members | bar: 2022-11-21 to 2022-12-12; 2023-01-02 to 2023-01-16
Identify 1st Oversight Board meeting date | bar: 2022-12-05 to 2022-12-12
Desk research - existing processes and materials | bar: 2022-11-21 to 2022-12-12; 2023-01-02
Audit reports | bar: 2022-11-21 to 2022-12-12; 2023-01-02 to 2023-01-30
Draft Charter | bar: 2022-11-21 to 2022-12-12; 2023-01-02 to 2023-01-09
High-level project plan | bar: 2022-11-21 to 2022-12-12; 2023-01-02 to 2023-01-09
Initial Stakeholder Map | bar: 2022-12-05 to 2022-12-12; 2023-01-02 to 2023-01-16
Communications | Oversight Board Members invitation | bar: 2022-12-12; 2023-01-02 to 2023-01-16
Oversight Board - 1st meeting - Scope sign off | bar: 2022-12-12; 2023-01-02 to 2023-01-30
Initial Communications Launch planning | bar: 2022-12-12; 2023-01-02 to 2023-01-23
Communications Plan | bar: 2023-01-02 to 2023-01-30
Initial Communications Launch | bar: 2023-01-23 to 2023-01-30
Stakeholder Engagement Planning | bar: 2023-01-02 to 2023-01-30
Ongoing Comms (e.g. cascade) | bar: 2023-01-23 to 2023-07-17; 2023-08-21 to 2023-11-20
Service Assessment Model Design | Draft SAM operating levels | bar: 2023-01-02 to 2023-03-20
SAM - check with… TBD | bar: 2023-01-02 to 2023-03-20
SAM operating levels approved | bar: 2023-03-27; 2023-04-17 to 2023-04-24
Data Collection | High Level data collection Plan | bar: 2023-01-02 to 2023-01-30
Detailed Data Collection Plan | bar: 2023-01-16 to 2023-02-13
Staffing and Activity Data Collection (Resource Audit) | bar: 2023-01-30 to 2023-03-06
Oversight Board - 2nd meeting - SAM and diagnose plan sign off | bar: 2023-03-27
Benchmarking data collection | bar: 2023-01-30 to 2023-04-17
Service Assessment Staff Briefing | bar: 2023-04-24 to 2023-05-08
Targetted SAM Interviews, Workshops, Surveys | bar: 2023-04-24 to 2023-07-03
Voice of Customers and Partners | bar: 2023-04-03 to 2023-06-12
Service Assessment | Current Operating Level Self Assessment | bar: 2023-05-01 to 2023-06-12
Data Analysis | bar: 2023-06-05 to 2023-07-10
Evidence Report (Diagnose Report) | bar: 2023-07-03 to 2023-07-17
Oversight Board - 3rd meeting - evidence gathering stage sign off | bar: 2023-07-10 to 2023-07-17
Design Activities | TBD | bar: 2023-08-21 to 2023-10-30
Oversight Board - 4th meeting - options report and prioritising recommendations
Implement | Develop high-level proposal for implementation | bar: 2023-10-30 to 2023-11-20
Recommendations Report and Implementation Plan | bar: 2023-11-20

## zzFeb-Apr OLD Engage Phase Plan (hidden)
| Phase: | Engage | [11 empty] | Diagnose | [11 empty] | Review Outputs |  |  |  | Design | [10 empty] | Implement
Week commencing: | time axis 2023-02-06 to 2023-11-20
Workstream: | Detailed activity: | 2023-02-06: Scope sign-off; 2023-02-13: Oxford Half Term; 2023-02-20: Gloucs Half Term; 2023-04-03: Easter (6 & 7/4 UAS Closure); 2023-04-10: Easter (10/4); 2023-04-24: Diagnose plan sign-off; 2023-05-01: Bank Hol; 2023-05-08: Bank Hol; 2023-05-29: Bank Hol Half Term; 2023-07-10: CI Conf; 2023-07-17: Evidence Report; 2023-07-24: Summer; 2023-07-31: Summer; 2023-08-07: Summer; 2023-08-14: Summer; 2023-08-21: Summer; 2023-08-28: Bank Hol Summer; 2023-10-23: Half Term; 2023-10-30: Options Report; 2023-11-20: Recommendations Rpt & Implementation Plan
Governance | OB Meeting 2 - 27 April - SAM and diagnose plan sign off | 2023-07-24: Oversight Board to review and consider outcomes of Diagnose Phase
Co-Chair Meetings | bar: 2023-02-20 to 2023-02-27; 2023-03-13; 2023-03-27; 2023-04-10; 2023-04-24 to 2023-05-01; 2023-05-15; 2023-05-29; 2023-06-12; 2023-06-26; 2023-07-10; 2023-08-21; 2023-09-04; 2023-09-18; 2023-10-02; 2023-10-16; 2023-10-30; 2023-11-13 to 2023-11-20
Focus MPRs | bar: 2023-02-27; 2023-04-10; 2023-05-01; 2023-05-29; 2023-07-03; 2023-09-04; 2023-10-02; 2023-10-30
Sponsor updates | bar: 2023-02-06; 2023-03-13; 2023-04-17
Service Assessment Model | Draft SAM operating levels | bar: 2023-02-06 to 2023-02-27
Form Check & Test Group | bar: 2023-02-06 to 2023-02-27
Request SAM input from Karen Sergiou | bar: 2023-02-20 to 2023-02-27
SAM development w Project Team | bar: 2023-02-20 to 2023-02-27
Initial mapping of existing evidence eg Rachel M report, audit | bar: 2023-02-27 to 2023-03-06
SAM induction meeting with Check and Test grp | bar: 2023-02-27
SAM development workshops w Check and Test Group | bar: 2023-03-06
Review output and refine SAM with project team | bar: 2023-03-13 to 2023-03-27
Draft evidence map for how SAM elements will be assessed | bar: 2023-03-20 to 2023-04-24
Present drafted SAM to Co-Chairs for review | bar: 2023-04-03 to 2023-04-10
Refine SAM based on feedback | bar: 2023-04-10
SAM sign-off by co-chairs | bar: 2023-04-10
Present SAM to Oversight Board (meeting 2) | bar: 2023-04-17 to 2023-04-24
Process improvement | Initial walkthrough with project team (MRP6: Manage Projects) | bar: 2023-02-13
Process walkthrough planning / prep | bar: 2023-03-13
Project team process improvement planning | bar: 2023-03-20
Comms planning for PUG/C&T group re workstream | bar: 2023-03-20
ROPOG mtg | bar: 2023-03-27
Form PUG | bar: 2023-04-10 to 2023-04-17
Invite PUG and C&T group to workshop(s) [no. tbd] | bar: 2023-04-17
Confirm attendance and workshop plans | bar: 2023-04-17 to 2023-04-24
Update OB on process improvement workstream planning | bar: 2023-04-24
RACI
Engagement and Info | Detailed stakeholder mapping | bar: 2023-02-06 to 2023-02-20
Gathering | Approach to engagement via Divisional Research Leads | bar: 2023-02-13
Meetings with Divisional Research Leads | bar: 2023-02-20 to 2023-02-27
Divisional engagement planning following feedback | bar: 2023-03-06 to 2023-03-13
Divisional comms re PI interviews | bar: 2023-03-13 to 2023-03-20
Interviews w PIs and Prof. Srvcs. Staff (PSS) | bar: 2023-03-20 to 2023-03-27; 2023-04-10 to 2023-04-24
Staffing and Activity Data Collection (Resource Audit) Survey Design | bar: 2023-03-13 to 2023-03-27
Staffing and Activity Data Collection (Resource Audit) RUN Survey | bar: 2023-04-03 to 2023-04-17
Analyse survey results | bar: 2023-04-10 to 2023-04-17
Present initial results to Oversight Board (meeting 2) | bar: 2023-04-24